ENGINEERING ROADMAP

FUTURE WORK

ARM-Nator Environment & Dependency Upgrade Plan

Purpose: Create a safe, repeatable path for upgrading the full desktop stack.

Baseline: Node 22.23.1 · pnpm 10.33.0 · Electron 41.7.2 · Angular 21.2.17 · Nx 22.7.1

Scope: Development, CI, release packaging, native playback, SQLite, and application dependencies.

Prepared: September 1, 2026

Recommendation. Use the current SQLite ABI incident as the trigger for environment hardening, then upgrade the stack in isolated waves. Do not perform a blind all-at-once dependency update.

# 1. Executive summary

ARM-Nator is a desktop application with two tightly coupled worlds: an Angular renderer and an Electron backend that owns SQLite, IPC, and native media playback. The current database failure is an environment-alignment problem, not a missing data problem. A successful long-term upgrade program must therefore keep the JavaScript framework, Electron runtime, native addons, Swift/MPV toolchain, CI, and release packaging in one documented compatibility system.

The plan below starts with reproducibility and test coverage, then moves from the runtime foundation outward. Each phase has an explicit exit gate so a regression can be isolated and rolled back without losing database data or media functionality.

# 2. Current baseline and upgrade surface

| Area | Current state | Long-term target |
| --- | --- | --- |
| JavaScript runtime | Node 22.23.1 locally; .nvmrc and CI use floating lts/*. | Exact Node version pinned in local tooling, CI, and package engines. |
| Package management | pnpm 10.33.0 is pinned through packageManager. | Keep exact pnpm pin; frozen-lockfile installs in every automated lane. |
| Desktop runtime | Electron 41.7.2 with nx-electron 22.0.0 and electron-builder 26.0.12. | One-version-at-a-time Electron upgrades with ABI and packaging smoke tests. |
| Renderer | Angular 21.2.17, Material 21.2.14, NgRx 21.1.1. | Angular packages upgraded in lockstep with supported Nx and TypeScript versions. |
| Database | SQLite via better-sqlite3 12.9.0; DB defaults to ~/.arm-nator/databases/arm-nator.db. | Automatic Electron-native rebuilds plus migration and backup compatibility tests. |
| Native playback | Embedded MPV and KSPlayer Metal addons; SwiftPM and node-gyp build steps. | Pinned build inputs, cache keys that include versions, and packaged-resource validation. |
| CI/release | macOS arm64 workflows; CI uses macos-15 and floating Node LTS. | Reproducible clean-checkout validation and release artifacts on a documented matrix. |

# 3. Guiding principles

- Isolation. Upgrade one compatibility boundary at a time; do not mix Electron, Angular, Nx, and native-player majors in one change.

- Reproducibility. Treat the lockfile, Node version, Electron version, architecture, Xcode version, and native build outputs as one release input.

- Runtime truth. Test the real desktop path through Electron, not only the Angular browser path.

- Data safety. Use copied E2E data directories and backups for migration tests; never use a user's live database as a test fixture.

- Operability. Prefer automated checks and documented rollback points over manual repair instructions.

# 4. Staged roadmap

## Phase 0 — Inventory and baseline

Establish a known-good reference before changing versions.

- Record the exact Node, pnpm, Electron, Angular, Nx, TypeScript, Xcode, Swift, macOS, and architecture versions used for a clean build.

- Run pnpm outdated and group candidates by runtime, framework, native, UI/player, and tooling categories.

- Capture baseline results for pnpm dev, pnpm test, pnpm build, and pnpm package.

- Document the DB path, ARM_NATOR_E2E_DATA_DIR behavior, native output paths, and release artifacts.

Exit gate: a clean checkout can reproduce the current baseline and the results are attached to the migration issue.

## Phase 1 — Deterministic environments

Remove version drift between a developer laptop, CI, and release packaging.

- Replace lts/* in .nvmrc and CI with an exact approved Node 22 patch version.

- Add a package engines constraint and a verify:environment command.

- Keep pnpm exact and require frozen-lockfile installs.

- Add cache keys that include Node, Electron, pnpm, lockfile, Xcode, and native runtime inputs.

- Keep pnpm's explicit native build allowlist and document why each allowed package is needed.

Exit gate: local development, CI, and release jobs report the same supported toolchain and architecture.

## Phase 2 — Native dependency lifecycle

Make the current ABI failure impossible to miss or repeat.

- Run electron-builder install-app-deps after install and before development when native dependencies are stale.

- Rebuild better-sqlite3 for the installed Electron version, not only for the host Node runtime.

- Build embedded_mpv.node and ksplayer_metal.node through the same documented Electron-targeted node-gyp lane.

- Add an Electron startup smoke test that opens SQLite and executes DB_GET_APP_PLAYLIST_METAS.

- Fail fast with a clear ABI error before the UI falls back to an empty playlist state.

Exit gate: pnpm install --frozen-lockfile followed by pnpm dev loads existing playlists without manual rebuild steps.

## Phase 3 — Test and observability foundation

Turn environment correctness into a measurable contract.

- Add DB open/read/write tests through the Electron bridge and database worker.

- Add migration tests against copied representative databases, including large content and FTS tables.

- Add startup traces for app path, database path, native module resolution, Electron ABI, and worker readiness.

- Add smoke coverage for playlist import, favorites, recently viewed items, global search, and app state.

- Add native-player smoke coverage for Embedded MPV and KSPlayer Metal on arm64.

Exit gate: a failed native module or database initialization produces a failing test and actionable log, not an apparently empty app.

## Phase 4 — Electron and native runtime upgrades

Upgrade the desktop runtime before changing the Angular application framework.

- Move Electron one supported major at a time and review its bundled Node ABI and Chromium changes.

- Update nx-electron and electron-builder only as required by the selected Electron version.

- Rebuild and test better-sqlite3, embedded MPV, and KSPlayer after every Electron change.

- Revalidate BrowserView, preload, IPC, Web API, GPU, Metal, and external-player behavior.

- Package a signed arm64 app and validate asar-unpacked native resources and runtime manifests.

Exit gate: the packaged app opens the existing database, loads playlists, and passes playback smoke tests on a clean macOS arm64 runner.

## Phase 5 — Angular, Nx, and TypeScript upgrades

Upgrade the renderer and build graph as a compatible framework set.

- Use Nx migrations for Nx and nx-electron changes; do not hand-edit generated migration effects without review.

- Upgrade Angular core, CLI, compiler, build, Material, ESLint integration, and schematics in lockstep.

- Upgrade TypeScript, Jest, SWC, esbuild, and ESLint only within the selected Angular/Nx compatibility window.

- Verify the dev server, production build, route behavior, environment file replacements, and Electron bridge typing.

- Review CommonJS allowlists and bundle budgets after each renderer upgrade.

Exit gate: Angular development and production builds are clean, tests pass, and the Electron window renders all workspace routes.

## Phase 6 — Application libraries and SQLite strategy

Refresh the remaining dependencies after the platform is stable.

- Update NgRx, RxJS, player libraries, HTTP clients, translation libraries, and UI utilities in small grouped changes.

- Review breaking changes against the app's provider, playlist, search, and playback contracts.

- Keep better-sqlite3 if automated rebuilds are reliable and performance remains appropriate for the catalog workload.

- Only prototype an N-API or WASM SQLite driver if native rebuild maintenance remains a recurring operational problem.

- Benchmark startup, import, FTS search, memory, and database migration behavior before considering a driver replacement.

Exit gate: dependency updates do not change user-visible playlist, search, favorites, or playback semantics without an explicit product decision.

## Phase 7 — Data migrations and release safety

Make schema evolution safe across future versions.

- Maintain forward-only, idempotent migrations with a migration ledger and clear logging.

- Test upgrades from a real legacy database copy, not only an empty database.

- Add backup/restore verification before destructive schema or content changes.

- Keep data-directory changes explicit and never silently create a second database because of an environment mismatch.

- Document rollback limits: application rollback is safe only when the database schema remains readable by the older version.

Exit gate: a representative existing database survives the upgrade, opens in the new app, and can be restored from backup.

## Phase 8 — CI, release, and maintenance cadence

Make the upgrade program sustainable after the initial migration.

- Use exact Node and pnpm versions in CI and include environment diagnostics in failed job artifacts.

- Separate lint/test/build validation from the heavier native and packaging lanes, while keeping a clean-checkout release job.

- Run security/patch updates continuously, minor updates monthly, and major runtime/framework updates as planned migrations.

- Use grouped dependency PRs with mandatory smoke tests; never auto-merge Electron or native dependency majors.

- Maintain an upgrade compatibility matrix and a short rollback note for each major runtime change.

Exit gate: a maintainer can perform the next upgrade from the documented procedure without rediscovering the ABI, database-path, or packaging traps.

# 5. Recommended dependency update order

| Order | Dependency group | Why this order |
| --- | --- | --- |
| 1 | Node, pnpm, package-manager tooling | Removes local/CI drift and establishes a stable host build environment. |
| 2 | Electron, nx-electron, Electron Builder | Defines the runtime ABI that every native addon must target. |
| 3 | better-sqlite3, node-gyp, MPV, KSPlayer | Rebuilds and validates the native boundary before framework changes. |
| 4 | Nx, Angular CLI/build, Angular, Material, NgRx | Keeps the renderer and workspace migrations coherent. |
| 5 | TypeScript, ESLint, Jest, SWC, esbuild | Aligns tooling after the framework migration has settled. |
| 6 | Player, HTTP, translation, and utility libraries | Limits application-level regressions to focused, reviewable groups. |
| 7 | Transitive/security updates | Cleans up remaining drift after compatibility-sensitive work is complete. |

# 6. Upgrade gates and rollback

- Gate 1. Create a migration branch from the known-good baseline and save the current lockfile and build results.

- Gate 2. After each dependency group, run the relevant focused tests before moving to the next group.

- Gate 3. Do not accept a green Angular build if the Electron DB smoke test or native-player checks fail.

- Gate 4. Keep the previous packaged app and database backup available until the new release passes real-data verification.

- Gate 5. If a phase fails, revert that phase only; do not reset unrelated user data or delete the live database.

# 7. Future-work backlog

| ID | Work item | Definition of done |
| --- | --- | --- |
| UPG-001 | Pin Node and CI environment | Exact Node version is shared by .nvmrc, package engines, CI, and documentation. |
| UPG-002 | Automate Electron native rebuilds | Fresh install and dev launch rebuild/validate better-sqlite3 automatically. |
| UPG-003 | Add environment doctor | One command reports versions, architecture, ABI, toolchain, and native outputs. |
| UPG-004 | Add Electron DB smoke test | The test opens SQLite through the worker and reads playlist metadata. |
| UPG-005 | Add native playback smoke lane | Embedded MPV and KSPlayer pass on clean macOS arm64 CI. |
| UPG-006 | Upgrade Electron in isolation | One Electron major upgrade passes startup, DB, playback, and packaging gates. |
| UPG-007 | Upgrade Angular/Nx in isolation | Renderer and workspace migrations pass build, lint, test, and route checks. |
| UPG-008 | Evaluate SQLite driver options | A benchmark report compares better-sqlite3 with N-API/WASM alternatives. |
| UPG-009 | Document data migration policy | Backup, migration, rollback, and compatibility rules are explicit. |
| UPG-010 | Establish maintenance cadence | Patch/minor/major update policy and ownership are documented. |

# 8. Definition of success

- A new developer can clone the repository, install with the documented command, and launch Electron without manual native repair.

- The app opens the existing SQLite database and displays playlists instead of silently showing an empty state.

- CI, local development, and release packaging use a documented, reproducible toolchain.

- Electron, Angular, Nx, native media, and database changes can be upgraded independently with clear gates.

- Real user data remains protected by backup, copied migration fixtures, and explicit rollback notes.

# Appendix — Key project locations

| Concern | Project location |
| --- | --- |
| Angular renderer | apps/desktop-ui/src and apps/desktop-ui/project.json |
| Electron backend | apps/electron-backend/src and apps/electron-backend/project.json |
| SQLite path and connection | libs/database/src/lib/path-utils.ts and connection.ts |
| Database worker | apps/electron-backend/src/app/workers/database.worker-connection.ts |
| Dependency versions | package.json and pnpm-lock.yaml |
| Native packaging | electron-builder.json and tools/packaging |
| CI/release | .github/workflows/ci.yml and release.yml |
| Angular environments | apps/desktop-ui/src/environments/environment.ts and environment.prod.ts |